## Internal Audit Checklist
MunichTech GmbH
Information Security Management System
Internal Audit Checklist (MT-ISMS-AUD-001)
Version | 1
Effective Date | 14 April 2026
Prepared By | Austin Bond, Junior GRC Consultant / Internal Auditor
Classification | STRICTLY CONFIDENTIAL — Audit Evidence
Framework Alignment | ISO/IEC 27001:2022 (Clause 9.2)
Audit Cycle: | FY2026 Q2 Pre-Certification Audit
Lead Auditor: | Austin Bond (Acting as independent internal auditor)
Auditee(s): | Head of Engineering, IT Security Lead, HR Manager
Audit Scope: | SaaS Platform (AWS eu-central-1) and Munich HQ Operations
Ref ID | ISO Clause / Annex A | Audit Test Procedure & Question | Expected Evidence (Artifacts) | Finding Result | Auditor Notes & Corrective Actions | CAP Owner | Target Date
AUD-01 | Clause 4.3 (Scope) | Verify that the ISMS scope boundary is accurately defined and that any exclusions are legally and technically justified. | Document MT-ISMS-SCO-001. Verification that AWS eu-central-1 is the only region utilized. | Conformity (C) | Scope document accurately excludes client-owned IT environments. AWS Organization SCPs confirmed to block resource creation outside of the eu-central-1 region. | N/A | N/A
AUD-02 | Clause 6.1.3 (Risk Treatment) | Confirm that executive management has formally accepted any residual risks that exceed the organization's defined risk appetite. | Document MT-ISMS-RR-001. Signature of the CEO on risks scoring 12 or higher. | Minor Non-Conformity (MiNC) | Risk RR-013 (Key Person Dependency) is scored as a 12 (High) and marked as Accepted. However the CEO signature column in the Risk Register was left blank. Auditee must obtain formal CEO sign-off within 7 days. | CISO / Head of Engineering | 21 April 2026
AUD-03 | A.5.24 (Incident planning) | Assess the organization's readiness to meet the NIS2 Article 23 reporting timeline in the event of a significant breach. | Document MT-NIS2-IRP-001. Tabletop exercise minutes proving the 24-hour BSI notification workflow is understood by the IT Security Lead. | Conformity (C) | Tabletop exercise conducted on 19 March 2026. Evidence provided showing the IT Security Lead successfully drafted a mock 24-hour early warning report using the BSI portal template. | N/A | N/A
AUD-04 | A.5.23 (Cloud services) | Verify that the AWS Shared Responsibility Model is actively managed and that cloud misconfigurations are continuously detected. | Live screenshare of the AWS Security Hub console in the production eu-central-1 account. | Conformity (C) | Auditor observed AWS Security Hub actively running the CIS AWS Foundations Benchmark. Overall compliance score is 94 percent. High-severity deviations are configured to trigger Slack alerts to the DevOps team. | N/A | N/A
AUD-05 | A.6.7 (Remote working) & A.8.1 (Endpoints) | Confirm that physical and technical controls are applied to remote MacBooks without violating German labor laws regarding employee monitoring. | Live screenshare of Microsoft Intune MDM policies. Counter-signed Works Council agreement for the deployment of CrowdStrike EDR. | Conformity (C) | Intune successfully enforces Apple FileVault encryption and a 5-minute screen lock. HR Manager provided the formal document ⁠MT-WorksCouncil-CrowdStrike-v1.2.pdf signed by the Betriebsrat explicitly permitting CrowdStrike deployment for security purposes only. | N/A | N/A
AUD-06 | A.8.10 (Information deletion) | Test the technical enforcement of DSGVO Article 17 (Right to Erasure) regarding aged client financial telemetry. | AWS S3 console configuration or Terraform scripts showing S3 Lifecycle rules applied to the production data lake buckets. | Opportunity for Improvement (OFI) | S3 Lifecycle policies are correctly configured to transition data to Glacier after 12 months and permanently delete after 24 months. OFI: The engineering team should implement automated unit tests to verify these Terraform rules are not accidentally removed during future CI/CD pipeline runs. | Head of Engineering | 13 July 2026
AUD-07 | A.8.31 (Separation of environments) | Ensure that actual client financial data or PII is never utilized in development or staging environments for testing purposes. | Review of the staging database schema. Interview with the Head of Engineering regarding data generation practices. | Conformity (C) | Head of Engineering demonstrated the use of Python Faker libraries to generate synthetic financial datasets for the CI/CD staging environment. Production RDS snapshots are explicitly blocked from being restored into the Dev AWS account via IAM boundaries. | N/A | N/A

## Grading Methodology
Grading Methodology
Conformity (C) | Opportunity for Improvement (OFI) | Minor Non-Conformity (MiNC) | Major Non-Conformity (MaNC)
The control is implemented effectively and evidence is readily available. | The control meets the standard, but maturity could be enhanced to reduce future risk. | A lapse in control implementation that does not immediately threaten the ISMS or client data. Requires a Corrective Action Plan (CAP) within 30 days. | A systemic failure or total absence of a required control. Poses an immediate threat to the ISMS, client data, or regulatory compliance. Halts certification readiness.

## Audit Sign-Off
AUDIT REPORT ATTESTATION
I hereby attest that this internal audit was conducted objectively and impartially in accordance with ISO 19011 guidelines.
Lead Auditor: Austin Bond
Signature: ___________________________
Date of Audit Completion: 14 April 2026
Acknowledged by CISO / Head of Engineering:
Signature: ___________________________
Date: 15 April 2026